## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  |  | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | SPRINT 1 |  | 40 | 40 | 0 |  |  |  |  | 100% | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30
1.1 | Sign-Up | Andrea | 5 | 5 | 0 |  | 2024-07-22 | 2024-07-26 | 5 | 100%: 100%; WEEK 1 M 22: 1; WEEK 1 T 23: 1; WEEK 1 W 24: 1; WEEK 1 R 25: 1; WEEK 1 F 26: 1
1,2 | Sign-In and Logout | Samuele | 15 | 15 | 0 |  | 2024-07-29 | 2024-07-31 | 3 | 100%: 100%; WEEK 2 M 29: 5; WEEK 2 T 30: 5; WEEK 2 W 31: 5
1.3 | Main articles | Agnese | 10 | 10 | 0 |  | 2024-07-30 | 2024-08-02 | 4 | 100%: 100%; WEEK 2 T 30: 3; WEEK 2 W 31: 3; WEEK 2 R 1: 2; WEEK 2 F 2: 2
1,4 | Article page | Rosapia | 10 | 10 | 0 |  | 2024-08-01 | 2024-08-02 | 2 | 100%: 100%; WEEK 2 R 1: 5; WEEK 2 F 2: 5
2 | SPRINT 2 |  | 70 | 70 | 0 |  |  |  |  | 100%: 100%
2.1 | Patient Dashboard | Andrea | 15 | 15 | 0 |  | 2024-08-05 | 2024-08-07 | 3 | 100%: 100%; WEEK 3 M 5: 5; WEEK 3 T 6: 5; WEEK 3 W 7: 5
2.2 | Medical Record | Rosapia | 20 | 20 | 0 |  | 2024-08-07 | 2024-08-09 | 3 | 100%: 100%; WEEK 3 T 6: 5; WEEK 3 W 7: 5; WEEK 3 R 8: 5; WEEK 3 F 9: 5
2.3 | Doctor List and Doctor profiles | Agnese | 15 | 15 | 0 |  | 2024-08-12 | 2024-08-16 | 5 | 100%: 100%; WEEK 4 M 12: 3; WEEK 4 T 13: 3; WEEK 4 W 14: 3; WEEK 4 R 15: 3; WEEK 4 F 16: 3
2.4 | Patient-Doctor Communication | Samuele | 20 | 20 | 0 |  | 2024-08-12 | 2024-08-16 | 5 | 100%: 100%; WEEK 4 M 12: 3; WEEK 4 T 13: 3; WEEK 4 W 14: 4; WEEK 4 R 15: 5; WEEK 4 F 16: 5
3 | SPRINT 3 |  | 50 | 50 | 0 |  |  |  |  | 100%: 100%
3.1 | GP request | Samuele | 5 | 5 | 0 |  | 2024-08-19 | 2024-08-21 | 3 | 100%: 100%; WEEK 5 M 19: 2; WEEK 5 T 20: 2; WEEK 5 W 21: 1
3,2 | Patient Treatments | Rosapia | 15 | 15 | 0 |  | 2024-08-21 | 2024-08-23 | 3 | 100%: 100%; WEEK 5 W 21: 5; WEEK 5 R 22: 5; WEEK 5 F 23: 5
3,3 | Calendar Access | Agnese | 20 | 20 | 0 |  | 2024-08-26 | 2024-08-29 | 4 | 100%: 100%; WEEK 6 M 26: 5; WEEK 6 T 27: 5; WEEK 6 W 28: 5; WEEK 6 R 29: 5
3,4 | Calendar Manage | Andrea | 10 | 10 | 0 |  | 2024-08-27 | 2024-08-30 | 4 | 100%: 100%; WEEK 6 T 27: 2; WEEK 6 W 28: 2; WEEK 6 R 29: 3; WEEK 6 F 30: 3
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 160 | 160 | 0 | 30 | 5.3333 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
[10 empty] | PLAN | 160 | 154.6667 | 149.3333 | 144 | 138.6667 | 133.3333 | 128 | 122.6667 | 117.3333 | 112 | 106.6667 | 101.3333 | 96 | 90.6667 | 85.3333 | 80 | 74.6667 | 69.3333 | 64 | 58.6667 | 53.3333 | 48 | 42.6667 | 37.3333 | 32 | 26.6667 | 21.3333 | 16 | 10.6667 | 5.3333
[10 empty] | ESTIMATE | 160 | 160 | 159 | 158 | 157 | 156 | 151 | 143 | 135 | 128 | 121 | 116 | 106 | 96 | 91 | 86 | 80 | 74 | 67 | 59 | 51 | 49 | 47 | 41 | 36 | 31 | 26 | 19 | 12 | 4
[10 empty] | HRS COMPLETED | 1 | 1 | 1 | 1 | 1 | 5 | 8 | 8 | 7 | 7 | 5 | 10 | 10 | 5 | 5 | 6 | 6 | 7 | 8 | 8 | 2 | 2 | 6 | 5 | 5 | 5 | 7 | 7 | 8 | 3
[10 empty] | HRS REMAINING | 160 | 159 | 158 | 157 | 156 | 151 | 143 | 135 | 128 | 121 | 116 | 106 | 96 | 91 | 86 | 80 | 74 | 67 | 59 | 51 | 49 | 47 | 41 | 36 | 31 | 26 | 19 | 12 | 4 | 1
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])+1

## Product Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
Product Backlog
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | ADDED BY
High | 1 | Account management | Sign-Up | Signing-Up as Doctor/Patient | Andrea
High | 1 | Account management | Sign-In and Logout | Sign-In as Doctor/Patient and Logout | Samuele
Low | 1 | Account management | Main articles | Users can read some main articles by accessing the homepage | Agnese
Low | 1 | Personal Area | Article page | Users can see more articles by accessing a dedicated page | Rosapia
High | 2 | Personal Area | Patient Dashboard | Patients can see their prescriptions and symptoms by accessing their dashboard | Andrea
High | 2 | Personal Area | Medical Record | Patients can see and manage their medical history and allergies by accessing their medical record | Rosapia
High | 2 | Personal Area | Doctor List and Doctor Profile | Patients can see doctor list with all the expertise information that doctors can edit in their own profiles | Agnese
High | 2 | Personal Area | Patient-Doctor Communication | Patients can add some doctors and start chatting with them | Samuele
High | 3 | Personal Area | GP request | Patients can send a doctor a request for them to become their GP | Samuele
High | 3 | Personal Area | Patient Treatments | Doctors and GP can manage their own patients' prescriptions | Rosapia
Medium | 3 | Treatment Management | Calendar Access | Patients can access a calendar and check their appointments | Agnese
Medium | 3 | Treatment Management | Calendar Manage | Doctors can access a calendar and manage their appointments | Andrea

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Sign-Up, Sign-In and Logout, Main articles, Article page | Account management | Signing-Up as Doctor/Patient, Sign-In as Doctor/Patient and Logout, Users can read some main articles by accessing the homepage, Users can see more articles by accessing a dedicated page | 40 | Completed | This sprint is the initial phase of the application, where we managed the correct working of the website and first features. | Completed | 40
High | 2 | Patient Dashboard, Medical Record, Doctor List and Doctor profiles, Patient-Doctor Communication | Personal Area | Patients can see their prescriptions and symptoms by accessing their dashboard, Patients can see and manage their medical histories and allergies by accessing their medical record, Patients can see doctor list with all their expertise information that doctors can edit in their own profiles, Patients can add some doctors and start chatting with them | 70 | Completed | In this sprint we start to develop the personal area of both Doctor and Patient. | Completed | 70
High | 3 | GP request, Patient Treatments, Calendar Access,Calendar Manage | Personal Area | Patients can send a doctor a request for them to become their GP, Doctors and GP can manage their own patients' prescriptions, Patients can access a calendar and check their appointments, Doctors can access a calendar and manage their appointments | 50 | Completed | In this sprint we finish the personal area features. | Completed | 50